## Basic Manual Gantt Chart
Tugas | Mulai | Selesai | Durasi | Start Date in Number Form | 43248 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Membuat Draft Proposal | 2018-05-28 | 2018-05-31 | 3
Membuat Revisi Proposal | 2018-06-04 | 2018-06-24 | 20
Libur Idul Fitri | 2018-06-13 | 2018-06-19 | 6
UTS TA 1 | 2018-06-25 | 2018-06-27 | 2
Melakukan Observasi & Studi Literatur | 2018-06-28 | 2018-07-20 | 22
Mengerjakan Bab 1 & Bab 2 | 2018-06-28 | 2018-07-23 | 25
UAS TA 1 | 2018-07-24 | 2018-07-26 | 2
Libur Semester | 2018-07-28 | 2018-08-19 | 22
Membuat Kuesioner & User Requirement | 2018-08-20 | 2018-09-09 | 20
Melakukan Perancangan Sistem | 2018-08-27 | 2018-09-23 | 27
Memulai Programming | 2018-09-24 | 2018-11-19 | 56
Program Testing | 2018-11-12 | 2018-11-17 | 5
Menyelesaikan Laporan | 2018-08-23 | 2018-12-02 | 101
Pengumpulan Laporan (Final) | 2018-12-02 | 2018-12-03 | 1
|  |  |  | Key: | Calculated Cell |  | Manual Entry Cell
[5 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.

## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 42576 | Use this number for the Minimum Bound of the Horizontal Axis to set the beginning of the chart.
Task One | 2016-07-25 | 2016-07-30 | 5 | 2.5 | 2.5 | 50%
Task Two | 2016-07-27 | 2016-08-01 | 5 | 3.75 | 1.25 | 75%
Task Three | 2016-07-27 | 2016-08-04 | 8 | 2 | 6 | 25%
Task Four | 2016-07-29 | 2016-08-06 | 8 | 8 | 0 | 100%
Task Five | 2016-08-01 | 2016-08-09 | 8 | 6 | 2 | 75%
Task Six | 2016-08-01 | 2016-08-05 | 4 | 1.4 | 2.6 | 35%
Task Seven | 2016-08-03 | 2016-08-10 | 7 | 1.75 | 5.25 | 25%
Task Eight | 2016-08-05 | 2016-08-12 | 7 | 4.9 | 2.1 | 70%
Task Nine | 2016-08-03 | 2016-08-09 | 6 | 0.9 | 5.1 | 15%
Task Ten | 2016-08-06 | 2016-08-10 | 4 | 2.4 | 1.6 | 60%
Task Eleven | 2016-08-07 | 2016-08-13 | 6 | 3.9 | 2.1 | 65%
Task Twelve | 2016-08-10 | 2016-08-16 | 6 | 1.5 | 4.5 | 25%
Task Thirteen | 2016-08-14 | 2016-08-19 | 5 | 1.5 | 3.5 | 30%
Task Fourteen | 2016-08-15 | 2016-08-23 | 8 | 4 | 4 | 50%
Task Fifteen | 2016-08-16 | 2016-08-26 | 10 | 4 | 6 | 40%
Task Sixteen | 2016-08-17 | 2016-08-28 | 11 | 3.85 | 7.15 | 35%
Task Seventeen | 2016-08-18 | 2016-08-29 | 11 | 1.65 | 9.35 | 15%
[7 empty] | Key: | Calculated Cell |  | Manual Entry Cell
[8 empty] | These cells will be automatically calculated based on the inputs on other cells. |  | These cells require manual input so the calculated cells have data to work with.